## Dashboard
Weekly Progress Dashboard (Linked)
Week Start Date
Week End Date
Completed Tasks |  | Total Tasks |  | Completion Rate
Progress by Day (Daily_Log + DayN_Done)
Day | Completed | Total | Rate
Day 1
Day 2
Day 3
Day 4
Day 5
Day 6
Day 7
Link Rule
Dashboard counts tasks from Daily_Log only (☐/☑). Day1_Done~Day7_Done are evidence logs and are excluded from completion rate.

## Daily_Log
Daily Task Log (Day blocks auto-prebuilt for one week)
Date | Day | Task ID | Task | Priority | Owner | Check | Status | Notes | Done Time
Day 1 - 2026-05-05
2026-05-05 | Day 1 | D1-01 | Confirm app_list.xlsx has 14 target apps | Medium | William | ☑ | Done | Config updated and validated | 14:37
2026-05-05 | Day 1 | D1-02 | Run 01_collect and verify outputs generated | Medium | William | ☑ | Done | 01_collect completed (14/14 apps) | 14:45
2026-05-05 | Day 1 | D1-03 | Run 02_clean and verify outputs generated | Medium | William | ☑ | Done | 02_clean completed | 14:55
2026-05-05 | Day 1 | D1-04 | Validate 14/14 app coverage and equal rows | Medium | William | ☑ | Done | Day1 checks passed | 15:15
2026-05-05 | Day 1 | D1-05 | Record Day 1 log and key metrics | Medium | William | ☑ | Done | Daily markdown log written | 15:17
2026-05-05 | Day 1 | D1-06 | Write daily summary and blockers | Medium | William | ☑ | Done | Day 1 summary and blockers recorded | 15:55
Day 2 - 2026-05-06
2026-05-06 | Day 2 | D2-01 | Build app-level base metrics table (avg/positive/low-star) | Medium | William | ☑ | Done | app_base_metrics.csv + scripts/06_insights/build_app_base_metrics.py | 20:32
2026-05-06 | Day 2 | D2-02 | Compute Bayesian adjusted rating and confidence | Medium | William | ☑ | Done | config/metrics.json + bayesian in build_health_score.py | 20:32
2026-05-06 | Day 2 | D2-03 | Implement momentum (period change or 8w slope) | Medium | William | ☑ | Done | build_health_score.py momentum | 20:32
2026-05-06 | Day 2 | D2-04 | Calculate app health score table for 14 apps | Medium | William | ☑ | Done | build_health_score.py | 20:32
2026-05-06 | Day 2 | D2-05 | Export app_health_score.csv and sanity-check ranking | Medium | William | ☑ | Done | reports/tables/app_health_score.csv + verify OK | 20:32
2026-05-06 | Day 2 | D2-06 | Write Day 2 summary and blockers | Medium | William | ☑ | Done | day2_2026-05-06.md | 20:32
Day 3 - 2026-05-07
2026-05-07 | Day 3 | D3-01 | Create app-level benchmark outputs (BQ2) | Medium | William | ☑ | Done | reports/tables/app_benchmark_bq2.csv | 20:48
2026-05-07 | Day 3 | D3-02 | Create publisher-level benchmark outputs | Medium | William | ☑ | Done | reports/tables/publisher_benchmark.csv | 20:48
2026-05-07 | Day 3 | D3-03 | Create flagship 7-app benchmark view | Medium | William | ☑ | Done | reports/tables/flagship_7_benchmark.csv | 20:48
2026-05-07 | Day 3 | D3-04 | Build volume vs rating scatter source table | Medium | William | ☑ | Done | reports/tables/volume_vs_rating_scatter.csv | 20:48
2026-05-07 | Day 3 | D3-05 | Draft Page 2 competitor findings bullets | Medium | William | ☑ | Done | reports/page2_competitor_findings_draft.md | 20:48
2026-05-07 | Day 3 | D3-06 | Write Day 3 summary and blockers | Medium | William | ☑ | Done | day3_2026-05-07.md + tracker | 20:48
Day 4 - 2026-05-27
2026-05-27 | Day 4 | D4-01 | Create themes.yml v1 dictionary | Medium | William | ☑ | Done | themes.yml v2 (18 themes, 13 neg + 5 pos, exclude rules) | 19:30
2026-05-27 | Day 4 | D4-02 | Run rule-based multi-label theme tagging | Medium | William | ☑ | Done | scripts/06_insights/build_review_themes.py | 19:32
2026-05-27 | Day 4 | D4-03 | Export reviews_with_themes dataset | Medium | William | ☑ | Done | reviews_with_themes.csv (10940 rows; coverage 45.2%) | 19:32
2026-05-27 | Day 4 | D4-04 | Compute low-star and positive theme rankings | Medium | William | ☑ | Done | theme_summary_overall/by_app + low_star_theme_summary | 19:33
2026-05-27 | Day 4 | D4-05 | Run quick manual QA on theme hits and refine once | Medium | William | ☑ | Done | v1→v2: Fun FP 462→382; Difficulty 29→113; Account→3 | 19:35
2026-05-27 | Day 4 | D4-06 | Write Day 4 summary and blockers | Medium | William | ☑ | Done | docs/daily_logs/day4_2026-05-27.md | 19:40
2026-05-27 | Day 4 | D4-07 | Manual theme validation sample review | High | William | ☒ | Cancelled | v1→v2 self-check already shipped on Day 4; second manual pass deferred to Phase 2 (LLM-assisted) | -
Day 5 - 2026-05-27
2026-05-27 | Day 5 | D5-01 | Compute Frequency/Impact/Severity by theme | Medium | William | ☑ | Done | frequency/impact/severity from theme_summary_overall.csv | 21:20
2026-05-27 | Day 5 | D5-02 | Calculate Priority Score and map P0-P3 | Medium | William | ☑ | Done | priority score + P0-P3 from quantile buckets + critical flag | 21:20
2026-05-27 | Day 5 | D5-03 | Build recommendation_matrix table | Medium | William | ☑ | Done | reports/tables/recommendation_matrix.csv | 21:21
2026-05-27 | Day 5 | D5-04 | Draft BQ5 product recommendations | Medium | William | ☑ | Done | day5_2026-05-27.md business recommendations section | 21:22
2026-05-27 | Day 5 | D5-05 | Prepare Page 4 recommendation source data | Medium | William | ☑ | Done | theme_priority_score.csv + theme_priority_by_app.csv | 21:21
2026-05-27 | Day 5 | D5-06 | Write Day 5 summary and blockers | Medium | William | ☑ | Done | docs/daily_logs/day5_2026-05-27.md | 21:22
2026-05-27 | Day 5 | D5-07 | Prepare Power BI source tables and relationship plan | High | William | ☑ | Done | Power BI source tables + relationship note generated | 21:23
Day 6 - 2026-05-28
2026-05-28 | Day 6 | D6-01 | Build Dashboard Page 1 (Executive Overview) | Medium | William | ☑ | Done | Tableau Page 1 built in Mobile_Game_Satisfaction_Tableau.twbx (Executive Overview). | 03:21
2026-05-28 | Day 6 | D6-02 | Build Dashboard Page 2 (Competitor Benchmarking) | Medium | William | ☑ | Done | Tableau Page 2 built in Mobile_Game_Satisfaction_Tableau.twbx (Competitor Benchmark). | 03:21
2026-05-28 | Day 6 | D6-03 | Build Dashboard Page 3 (Pain Point/Positive Driver) | Medium | William | ☑ | Done | Tableau Page 3 built in Mobile_Game_Satisfaction_Tableau.twbx (Theme Insights). | 03:21
2026-05-28 | Day 6 | D6-04 | Build Dashboard Page 4 (Product Recommendation) | Medium | William | ☑ | Done | Tableau Page 4 built in Mobile_Game_Satisfaction_Tableau.twbx (Product Recommendation). | 03:21
2026-05-28 | Day 6 | D6-05 | Draft insight report v1 from BQ1-BQ5 | High | William | ☑ | Done | reports/每日复盘/User_Satisfaction_Insight_Report.md + .pdf (bilingual, 9 sections) | 20:50
2026-05-28 | Day 6 | D6-06 | Write Day 6 summary and blockers | Medium | William | ☑ | Done | docs/daily_logs/day6_2026-05-28.md | 20:52
2026-05-28 | Day 6 | D6-07 | Add Data Honesty & Limitations section to insight report | High | William | ☑ | Done | Limitations & Data Honesty section integrated into insight report §7 | 20:52
Day 7 - 2026-05-11
2026-05-11 | Day 7 | D7-01 | Finalize README/portfolio-facing narrative | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-02 | Capture dashboard screenshots for deliverables | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-03 | Prepare resume bullets and interview storyline | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-04 | Do end-to-end QA pass on outputs and links | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-05 | Freeze Day 1-7 deliverable package | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-06 | Write Day 7 summary and blockers | Medium | William | ☐ | Todo
2026-05-11 | Day 7 | D7-07 | Freeze public portfolio version and clean placeholders | High | William | ☐ | Todo

## Day1_Done
Day 1 Completion Log
Date | 2026-05-05 |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Run | Pipeline step executed | 01_collect + 02_clean | Done | scripts/01_collect, scripts/02_clean
Run | Run time | 2026-05-05 14:55:58 | Done | reports/quality_report.csv
Validation | raw_rows | 16800 | Done | data/raw/google_play_reviews_raw.csv
Validation | clean_all_rows | 15290 | Done | data/processed/clean_all_languages.csv
Validation | clean_en_rows | 10956 | Done | data/processed/clean_en_only.csv
Validation | english_share | 0.6521 | Done | calc: clean_en/raw
Validation | date_min | 2024-02-12 00:12:16 | Done | raw at
Validation | date_max | 2026-05-04 14:37:17 | Done | raw at
Quality | Key quality metric #1 | duplicate_rate=0.0 | Done | reports/quality_report.csv
Quality | Key quality metric #2 | empty_text_rate=0.0001 | Done | reports/quality_report.csv
Output | Primary output file #1 | google_play_reviews_raw.csv | Done | data/raw/
Output | Primary output file #2 | quality_report.csv | Done | reports/
Summary | Day conclusion | Day 1 checks passed; ready for Day 2 | Done | docs/daily_logs/day1_2026-05-05.md

## Day2_Done
Day 2 Completion Log
Date |  |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Metrics | avg_rating_by_app | see app_base_metrics | Done | reports/tables/app_base_metrics.csv
Metrics | positive_share_by_app | computed | Done | app_base_metrics.csv
Metrics | low_star_share_by_app | computed | Done | app_base_metrics.csv
Metrics | bayesian_adjusted_rating | global_mean 3.676 | Done | app_health_score.csv
Metrics | confidence | all 1.0 (n≥513) | Done | app_health_score.csv
Metrics | momentum | weekly slope / fallback | Done | app_health_score.csv
Output | app_health_score.csv | 14 rows | Done | reports/tables/app_health_score.csv
Validation | ranking_sanity_check | VERIFICATION OK + rank review | Done | verify script / manual
Summary | day_conclusion | day2_2026-05-06.md | Done | docs/daily_logs/

## Day3_Done
Day 3 Completion Log
Date |  |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Output | app_benchmark_bq2.csv | 14 apps | Done | reports/tables/app_benchmark_bq2.csv
Output | publisher_benchmark.csv | 8 publishers | Done | reports/tables/publisher_benchmark.csv
Output | flagship_7_benchmark.csv | 7 apps | Done | reports/tables/flagship_7_benchmark.csv
Output | volume_vs_rating_scatter.csv | 14 apps | Done | reports/tables/volume_vs_rating_scatter.csv
Validation | benchmark_consistency_check | merged from base+health | Done | same grain as Day 2 tables
Summary | day_conclusion | day3 log + Page2 draft | Done | docs/daily_logs/day3_2026-05-07.md

## Day4_Done
Day 4 Completion Log
Date | 2026-05-27 |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Config | themes.yml_created | 18 themes (13 neg + 5 pos), v2 with exclude rules | Done | config/themes.yml
Output | reviews_with_themes.csv | 10940 rows, multi-label | Done | data/processed/reviews_with_themes.csv
Metrics | theme_coverage_rate | 45.2% (≥1 theme) | Done | reports/tables/theme_summary_overall.csv
Metrics | low_star_theme_topN | Fun 12.2%; Crash 8.1%; Loading 5.7%; Pay-to-win 3.9%; Difficulty 3.6% | Done | reports/tables/low_star_theme_summary.csv
Metrics | positive_theme_topN | Fun n=3567 share=32.6%; Story n=519; Visual n=239; Social n=230 | Done | reports/tables/theme_summary_overall.csv
Validation | manual_theme_QA_round1 | v1→v2 self-check done; D4-07 cancelled, second pass deferred to Phase 2 | Cancelled | reports/tables/theme_validation_sample.csv
Summary | day_conclusion | Theme pipeline shipped; Crash rating_gap +1.28; Loading +1.08 → Day 5 Priority | Done | docs/daily_logs/day4_2026-05-27.md
Task ID | D4-07 |  | Todo
Task Name | Manual theme validation sample review
Description | Manually review a sample of 100 low-star reviews and 50 high-star reviews to check false positives, false negatives, missing keywords, and obvious misclassification cases in the rule-based theme tagging.
Expected Output / Evidence | docs/theme_validation_notes.md; Updated config/themes.yml if keywords or exclude_keywords are refined
Purpose | Supports Theme Taxonomy and makes rule-based classification more defensible for DA/BA interview discussion.

## Day5_Done
Day 5 Completion Log
Date | 2026-05-27 |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Metrics | frequency | theme_share (global) / theme_share_in_app (app-level) | Done | reports/tables/theme_priority_score.csv
Metrics | impact | max(rating_gap, 0) for negative themes | Done | reports/tables/theme_priority_score.csv
Metrics | severity | share_low_1_2 | Done | reports/tables/theme_priority_score.csv
Metrics | priority_score | norm(freq)×norm(impact)×norm(severity)×1.5^critical | Done | reports/tables/theme_priority_score.csv
Output | recommendation_matrix.csv | 8 rows (P0+P1), owner/action/30-day-goal included | Done | reports/tables/recommendation_matrix.csv
Output | P0_P1_P2_P3_table | theme_priority_score.csv with priority_bucket | Done | reports/tables/theme_priority_score.csv
Summary | day_conclusion | Day 5 BQ5 delivered; backlog priorities ready for Page 4 | Done | docs/daily_logs/day5_2026-05-27.md
Task ID | D5-07 |  | Todo
Task Name | Prepare Power BI source tables and relationship plan
Description | Confirm all dashboard-ready tables are exported and named consistently before Power BI build; prepare relationship plan for app-level, publisher-level, theme-level, and recommendation-level tables.
Expected Output / Evidence | reports/tables/app_summary.csv; reports/tables/publisher_summary.csv; reports/tables/health_score.csv; reports/tables/theme_summary.csv; reports/tables/low_star_theme_summary.csv; reports/tables/positive_theme_summary.csv; reports/tables/app_theme_matrix.csv; reports/tables/recommendation_matrix.csv; docs/powerbi_data_model_notes.md
Purpose | Reduces Day 6 workload and avoids dashboard blocking due to messy source tables.

## Day6_Done
Day 6 Completion Log
Date | 2026-05-28 |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Dashboard | page1_executive | Tableau Page 1 complete (Executive Overview). | Done | reports/每日复盘/Mobile_Game_Satisfaction_Tableau.twbx | dashboard_page1.png captured
Dashboard | page2_competitor | Tableau Page 2 complete (Competitor Benchmark). | Done | reports/每日复盘/Mobile_Game_Satisfaction_Tableau.twbx | dashboard_page2.png captured
Dashboard | page3_themes | Tableau Page 3 complete (Theme Insights). | Done | reports/每日复盘/Mobile_Game_Satisfaction_Tableau.twbx | dashboard_page3.png captured
Dashboard | page4_recommendation | Tableau Page 4 complete (Product Recommendation). | Done | reports/每日复盘/Mobile_Game_Satisfaction_Tableau.twbx | dashboard_page4.png captured
Report | insight_report_v1 | Bilingual 9 sections; 8 embedded figures; ~1.4 MB PDF | Done | reports/每日复盘/User_Satisfaction_Insight_Report.pdf
Validation | visual_QA | All 8 PNGs regenerated from CSV; visual sanity check OK | Done | reports/每日复盘/figures/
Summary | day_conclusion | Day 6 dashboard + report deliverables complete; Tableau build finished on macOS. | Done | docs/daily_logs/day6_2026-05-28.md
Task ID | D6-07 |  | Done
Task Name | Add Data Honesty & Limitations section to insight report
Description | Add a short limitations section: Google Play reviews are public samples (not full user population); metrics are review-based proxy signals; no internal retention/conversion/revenue/DAU or causal impact analysis.
Expected Output / Evidence | Limitations section in reports/Mobile_Game_Review_Analytics_Insight_Report.docx; same limitation note summarized in README
Purpose | Aligns with design doc and prevents overclaiming business impact.

## Day7_Done
Day 7 Completion Log
Date |  |  | Owner | William
Section | Metric | Value | Status | Evidence/File | Notes
Portfolio | README_update |  | Todo
Portfolio | dashboard_screenshots |  | Todo
Career | resume_bullets |  | Todo
Career | interview_storyline |  | Todo
QA | final_package_QA |  | Todo
Output | deliverable_freeze |  | Todo
Summary | day_conclusion |  | Todo
Task ID | D7-07 |  | Todo
Task Name | Freeze public portfolio version and clean placeholders
Description | Remove temporary placeholders, verify file paths, check dashboard screenshots, ensure README/report wording is professional, and create clean public-facing package.
Expected Output / Evidence | portfolio/Project_README.md; portfolio/Dashboard_Screenshots.pdf; portfolio/Insight_Report.pdf; portfolio/Methodology_Appendix.pdf; private_job_prep/Resume_Bullets.docx; private_job_prep/Interview_Story.docx
Purpose | Separates public portfolio materials from private job-prep materials.